## 2014-06-30
30/06/2014 Daily scrum meeting( Standup meeting)
| Done | impendend | To DO | Parking lot
Joy | 1. install Ubuntu + Vmware 2.uncompress QT 3.uncompress cross-compiler 4.5.1 | 1)how to configurate Cross-compiler | 1) master JIRA operation 1) update progress , 2) assign task to me 3) create issue 4) view dashboard
suntao | 1. how to use git hub. Clone, pull, (push not complete) 2.Eclipse + QT installation | 1) couldn't assign the task to me | 1)Github submit 2)install BoUM | 1) concurance take the same task
lindong | 1.ubuntu 14.04.4 + eclipse with C++ + BOUML 2. arm-linux-gcc_4.5.1 toolschain |  | 1) install BOUML 2) draw the use-case
James | 1.st32 console
Gabriel | 1. install eclipse + BoUML 2. crosse complier configuration 3.Github + JIRA | 1) tiny 4412 could be pinged by other host
shifeng | 1.Github | None | 1.JIRA(Need to be clarified with more detail task and creteria of DONE) 2.UML -use case( Template)

## 2014-07-01
30/06/2014 Daily scrum meeting( Standup meeting)
| Done | impendend | To DO | Parking lot
Joy
suntao
lindong
James
Gabriel
shifeng

## 2014-07-02
30/06/2014 Daily scrum meeting( Standup meeting)
| Done | impendend | To DO | Parking lot
Joy
suntao
lindong
James
Gabriel
shifeng