## Guidance
Title | Postmortem Meeting
Summary | This is postmortem meeting of ADE. This meeting will be performed either at the end of a project, or at certain pre-determined project phases such as the end of specified phases.
Guideline | 1. Identifying those things that went well with a project so that they are repeated in future projects where applicable. 2. Identifying those things that did not go well so that project planning, processes, and communication may be improved allowing future projects to benefit favorably from the improvements made. 3. Every participant is peer and open to talk his opinions. 4. To use minimum effort and cost to deal with the maximum problem.
Participants | 1. Project manager 2. Project Architect 3. Team member 4. Stackholders (in the future) 5. Customer (in the future)
Steps | 1. Announce the meeting enough in advance. 2. Collect and Agreed on the topics by every participant. 3. Team performance evaluation from every participant before the meeting. 4. Log the goods, issues and ways might be helpful by every participant before the meeting. 5. Discuess the goods, issues and ways on the meeting. 6. send out the outcomes from this meeting to all participants.

## Report
Project Information
Project Name | EDA ADE DEV 2010
Milestone | ADE Release Plan Completed
Team Performance Evaluation
Judge | Poor |  |  | average |  |  |  | outstanding
David | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Steven | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
James | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Destin | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Alex | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Over All | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Things that went well
Member | Opinion
Destin | Team brainstorming is excellent. Actually we have a lot of great idea that have been logged in our backlog.
Destin | Task execution is good. Once we are cleared about the task, we can quickly to move on until it is been done.
James | The team has done a lot since the members were onborad at the end of last year.
Alex | we have a great start environment, a lot of codes and documents for us.
Things that did not go well
Member | Opinion |  |  |  | Possible solution to make progress
Destin | The task clarification is not good. Sometimes we are too late to make the task clear. |  |  |  | 1. We separate task to several scenario as early as possible. 2. The owner of the backlogs will be changed to all team (James, Steven, Destin, Alex), so that everybody will take the responsibility to maintain the backlogs, by doing so everyone could raise and check the issues easily.
Destin | Resource is not enough to cover some exception. For instance, some time we need to take some long term trainning like TSP/PSP, PMP, ITIL, etc.. While doing so, the task progress will be delayed obviously, If we have more resources we can cover eachother's task when someone is out for training. |  |  |  | need whole team's brain…
Alex | too many kind of different task |  |  |  | focus on core task
James | Communicate with each other more. Clearify the
Outcomes (will be tracked on the meeting)
Action | [8 empty] | Possible Owner
Try to connect the StarTeam and CaliberRm Server. | [8 empty] | Cao, Yin Chao
Plan needs to have buffer, we can mark the resource's calander day or make a task and assign to the resource for the exception when the owner can not perform a task.
Change the meeting name to Peformance around table.
Log more details in the backlogs about the Alex's opinion on the ADEGen.
Reserve the Friday even only for emergency meeting.